## Summary
YEAR PROJECTS WERE COMPLETED/DESIGNED | SRID LOCAL FUNDING TOTAL PROJECT COST MANAGED BY FACILITIES | SRID LOCAL FUNDING TOTAL PROJECT COST MANAGED BY CAMPUS | BC101 FUNDING TOTAL PROJECT COST MANAGED BY FACILITIES | BC101 FUNDING TOTAL PROJECT COST MANAGED BY CAMPUS |  |  | OTHER FUNDING TOTAL PROJECT COST MANAGED BY FACILITIES | [7 empty] | OTHER FUNDING TOTAL PROJECT COST MANAGED BY CAMPUS | TOTAL FUNDING PROJECT COST
2012-2013 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [6 empty] | 0 | 0
2013-2014 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 | 0
2014-2015 | 0 | 0 | 0 | 0 |  |  | 0 | [7 empty] | 0 | 0
Total Project Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2012-2013
Bakersfield College 2012-2013 Scheduled Maintenance and Capital Projects | Project Type | Org Code | Budget Cost | Actual Cost | SRID Funding | BC101 Funding | Other Funding | Assigned Planner/PM | SRID Code/Source | Project Status | Projected Construction Start Date | Projected Occupancy Date | Funding Capital Outlay
Facilities Managed Projects
Humanities Upgrades | SM | [6 empty] | Craig |  | Completed
Administration Building Upgrades | SM | [6 empty] | Craig |  | Completed
Gymnasium Upgrades | SM | [6 empty] | Craig |  | Completed
Student Services Upgrades | SM | [6 empty] | Craig |  | Completed
Language Arts Upgrades | SM | [6 empty] | Craig |  | Completed
Math Science Electronic Classroom Update | SM | [6 empty] | Daniel |  | Completed
Campus Wide Emergency Phones Removal | SM | [6 empty] | Daniel |  | Completed
Fine Arts Electrical Upgrades | SM | [6 empty] | Joe |  | Completed
FACE HVAC Replacement | SM | [6 empty] | Joe |  | Completed
Library Roof | SM | [6 empty] | Daniel |  | Completed
GET Project | SM | [6 empty] | Daniel |  | Completed
Forum Seating | SM | [6 empty] | Daniel |  | Completed
EMS Phase 1 | SM | [6 empty] | Joe |  | Completed
Main Gym Bleacher Replacement | SM | [6 empty] | Craig |  | Completed
SAM Move Out | Capital | [6 empty] | Craig |  | Completed
Facilities Managed Project cost totals |  |  |  | 0 | 0 | 0 | 0
Campus Managed Projects
Student Services Lab Room #151 | SM | [6 empty] | Craig |  | Completed
Gym Floor Resurfacing | SM | [6 empty] | Craig |  | Completed
Haley Entrance Asphalt Repair | SM | [6 empty] | Craig |  | Completed
Super vault Tank Painting | SM | [6 empty] | Craig |  | Completed
Remove Transformers from INDT Parking and Tank yard | SM | [6 empty] | Craig |  | Completed
Mail Room Relocation | SM | [6 empty] | Craig |  | Completed
Allied Health | SM | [6 empty] | Craig |  | Completed
Library Generator Repair | SM | [6 empty] | Craig |  | Completed
AST Floor Repair | SM | [6 empty] | Craig |  | Completed
FACE Building Carpet | SM | [6 empty] | Craig |  | Completed
Administration Building Enrollment Office Flooring Replacement | SM | [6 empty] | Craig |  | Completed
Main Gym Floor Resurface | SM | [6 empty] | Craig |  | Completed
Replace Flashing on Admin Building Roof | SM | [6 empty] | Craig |  | Completed
Fine Arts Building Roof Leak | SM | [6 empty] | Craig |  | Completed
Bakersfield College 2012-2013 Scheduled Maintenance and Capital Projects | Project Type | Org Code | Budget Cost | Actual Cost | SRID Funding | BC101 Funding | Other Funding | Assigned Planner/PM | SRID Code/Source | Project Status
Levinson Hall Room #40 Wall Repair/Roof Repair | SM | [6 empty] | Craig |  | Completed
Veteran Room | SM | [6 empty] | Craig |  | Completed
Child Development Center | SM | [6 empty] | Craig |  | Completed
Gym Floor Covering | SM | [6 empty] | Craig |  | Completed
Credit Union Sign | SM | [6 empty] | Craig |  | Completed
Fascia Replacement Humanities and Campus Center Buildings | SM | [6 empty] | Craig |  | Completed
Main Gym Temp Bleachers | SM | [6 empty] | Craig |  | Completed
Benches at Library | SM | [6 empty] | Craig |  | Completed
Parking Dispensers | SM
FACE Gas Leak | SM | [6 empty] | Craig |  | Completed
Ceiling Tile Screw Installation at Admin. Hallway and Fine Arts Building | SM | [6 empty] | Craig |  | Completed
Fine Arts Room 1 Exterior wall Repair | SM | [6 empty] | Craig |  | Completed
Simplex Site Identification | SM | [6 empty] | Craig |  | Completed
Book Store Exterior Stairs | SM | [6 empty] | Craig |  | Completed
AST Asphalt | SM | [6 empty] | Craig |  | Completed
Window Treatments SS151 | SM | [6 empty] | Craig |  | Completed
Campus Managed Project cost totals |  |  |  | 0 | 0 | 0 | 0
2012-2013 Total Project cost totals |  |  |  | 0 | 0 | 0 | 0

## 2013-2014
Bakersfield College 2013 - 2014 Scheduled Maintenance and Capital Projects | Project Type | Org Code | Budget Cost | Actual Cost | State Funding | SRID Funding | BC101 Funding | Other Funding | Assigned Planner/PM | Project Status | Projected Construction Start Date | Projected Occupancy Date | Funding Capital Outlay
Facilities Managed Projects
Campus Center Modernization & Asbestos Abatement | Capital | [7 empty] | Craig | In Design
Performing Arts Modernization | Capital | [7 empty] | Joe | In Construction
Performing Arts East Side Improvements | Capital | [7 empty] | Craig | In Design
ADA Path of Travel | SM | [7 empty] | Craig | In Design
Face Building Upgrades | SM | [7 empty] | Craig | In Construction
Science and Engineering Upgrades | SM | [7 empty] | Craig | In Construction
Business Education Upgrades | SM | [7 empty] | Craig | In Construction
Fine Arts Upgrades | SM | [7 empty] | Craig | In Construction
Administration Store Front Door Replacement | SM | [7 empty] | Craig | Completed
Science and Engineering Re Roof | SM | [7 empty] | Daniel | In Construction
Central Chiller Plant Replacement | Capital | [7 empty] | Craig | In Design
Campus Wide Water and Gas Line Replacement | Capital | [7 empty] | Craig | In Design
Campus Wide Access Hardware | SM | [7 empty] | Craig | In Design
LA Storefront Door Replacement | SM | [7 empty] | Craig | In Construction
SS Storefront Door Replacement | SM | [7 empty] | Craig | In Construction
BC M&O Building | SM | [7 empty] | Craig | In Design
BC Gym AC Upgrade | SM | [7 empty] | Craig | In Design
BC Student Services Elevator | SM | [7 empty] | Craig | In Design
Thermal Energy Storage | Capital | [7 empty] | Craig | Completed
ADA Parking Upgrade NE Parking Lot | SM | [7 empty] | Joe | In Design
Baseball Clubhouse Phone/Fiber Conduit | SM | [7 empty] | Daniel | Completed
LA Basement Fireproofing | SM | [7 empty] | Craig | In Design
North East Shade Structure | SM | [7 empty] | Joe | In Design
EMS Phase 2 | SM | [7 empty] | Craig | In Design
Air Handler Replacement SS, MS | SM | [7 empty] | Craig | In Design
Math Science Roof Repairs | SM | [7 empty] | Joe | Completed
PG&E Energy Projects | SM | [7 empty] | Craig | In Design
Facilities Managed Project cost totals |  |  | 0 | 0 | 0 | 0 | 0 | 0
Campus Managed Projects
SS Room #3 Lab Room | SM | [7 empty] | Craig | In Construction
MS Room 3, 4 Stem Program Center | SM | [7 empty] | Craig | In Construction
Bakersfield College 2013 - 2014 Scheduled Maintenance and Capital Projects | Project Type | Org Code | Budget Cost | Actual Cost | State Funding | SRID Funding | BC101 Funding | Other Funding | Assigned Planner/PM | Project Status
MS Room #11 Stem Program | SM | [7 empty] | Craig | In Construction
Wrestling Room Painting Lockers | SM | [7 empty] | Craig | Completed
Pool Pump | SM | [7 empty] | Craig | In Design
Bookstore Ext. Stairs | SM | [7 empty] | Craig | Completed
Filinson Bathroom Interior Painting | SM
Bus Turnaround at Sam East | SM | [7 empty] | Craig | In Design
Palm Tree at Bus Turnaround | SM | [7 empty] | Craig | In Design
Campus Wide Bollards | SM | [7 empty] | Craig | In Design
Campus Managed Project cost totals |  |  | 0 | 0 | 0 | 0 | 0 | 0
2012-2013 Total Project cost totals |  |  | 0 | 0 | 0 | 0 | 0 | 0
**Note: Projects in the design phase will have the approved funding source when the PPR is signed off.

## 2014-2015
Bakersfield College 2014 - 2015 Scheduled Maintenance and Capital Projects | Project Type | Org Code | Budget Cost | Actual Cost | State Funding | SRID Funding | BC101 Funding | Other Funding | Assigned Planner/PM | Project Status | Projected Construction Start Date | Projected Occupancy Date | Funding Capital Outlay
Facilities Managed Projects
Business Bldg Parking Lot Resurfacing | SM | [7 empty] | Craig | On Hold
Southwest Parking Lot Resurfacing | SM | [7 empty] | Craig | On Hold
Southeast Stadium Roadway Repairs | SM | [7 empty] | Craig | On Hold
Southeast Parking Lot Resurfacing | SM | [7 empty] | Craig | On Hold
Southeast (Stadium) Parking Lot Lighting | SM | [7 empty] | Craig | On Hold
Student Services Modernization | Capital | [7 empty] | Craig | On Hold
Campus Wide Way-Finding Signage Replacement | SM | [7 empty] | Craig | On Hold
Language Arts Modernization | Capital | [7 empty] | Craig | On Hold
Facilities Managed Project cost totals |  |  | 0 | 0 | 0 | 0 | 0 | 0
Campus Managed Projects
Summer 2015 Building Upgrades Projects (TBD) | SM | [7 empty] | Craig | On Hold
Stem Grant Projects | SM | [7 empty] | Craig | On Hold
Room Occupancy Signage/Exit Routing | SM | [7 empty] | Craig | On Hold
Track and Field Turf Replacement | SM | [7 empty] | Craig | On Hold
Campus Managed Project cost totals |  |  | 0 | 0 | 0 | 0 | 0 | 0
2012-2013 Total Project cost totals |  |  | 0 | 0 | 0 | 0 | 0 | 0
**Note: Projects in the design phase/on hold, will have the approved funding source when the PPR is signed off.