**2018-2021 Strategic Directions**

***October 12, 2017***

**WHAT:**

In 2015 Bakersfield College completed the three-year strategic plan that would provide the direction through June 30, 2018. As we approach the final months of that plan, it is time to evaluate, develop, and prepare for the next three-year cycle of our strategic plan.

**WHO:**

***Strategic Directions Core Team***

Lead: Todd Coston, Information Technology

Grace Commiso, Interim Dean of Counseling, Student Services

Liz Rozell, Dean of Instruction, Academic Affairs

Bill Moseley, Dean of Instruction, AIQ Representative

Jessica Wojtysiak, Faculty, AIQ Representative

Marcelyn Allen, Faculty

Teresa Mcallister, Faculty

Aricia Leighton, Web Team

Somaly Boles, Clerical Support

***Strategic Directions Task Force (includes Core Team)***

Academic Senate: Need 3 members

Classified Union President or designee and two CSEA appointees

SGA President or designee and one student appointee

Management Leadership Association: Sue Vaughn

CCA chair or designee

Executive Leadership: Vice President of Affairs or designee, Vice President of Student Affairs or designee, Vice President of Finance or Administrative Services or designee

Data Leads: Dean of Institutional Research or designee

Equity: Cornelio Rodriguez (?)

Rural Initiatives representative: Rich McCrow (?)

Members at large: Two members previously

**DELIVERABLES:**

* A *Strategic Directions 2018 - 2021* document that discusses the development process; identifies key challenges; and describes college goals, data strands, and initiatives.
* Website that includes the primary document as well as all the supporting materials.

**DEADLINE:** March for presentation and voting

**HOW:**

|  |  |
| --- | --- |
| **Timeline** | **Core Team Lays the Foundation** |
| September  and  October | **Begin to build example initiatives within each Direction using current institutional documents.**   * Liz – Pathways initiatives for all five Directions. * Grace – Example initiatives Direction #2. * Todd – Example initiatives Direction #3. * Teresa – Example initiatives Direction #4. * Marcelyn - Example initiatives Direction #5.   **Develop SD web site** |
|  | **Strategic Directions Task Force Begins Work** |
| November  and  December | **Committee Involvement**   * Academic Senate (date/lead) * Curriculum (date/lead) * Assessment (date/lead) * Program Review (date/lead) * ISIT (date/lead) * Facilities (date/lead) * FCDC (date/lead) * AIQ (date/lead) * College Council (date/lead) * Admin Council (date/lead) * PDC (date/lead) * Budget (date/lead)   **Focus Groups**   * Main Campus (invite all) (date/lead) * Delano Campus (invite all) (date/lead) |
| January  and February | **Core Team**   * Evaluate, organize, and finalize initiatives based on feedback from Nov and Dec work. |
| March | **Further refinement**   * Solicit feedback from Pres. Cabinet and further refine initiatives. * Prepare Final Report to share with College Council for approval and vote. |
| April | **Approval and Vote**   * Academic Senate Vote (need dates) * College Council first read (April 6th) and vote (April 20th). |
| May | **Presentation to College Community** |