| Revised 2015 Midterm Report Schedule |
| --- |
| Timeline | Activity | People Responsible |
| Mid-September | Training Workshops(pick one) Friday, September 12, 11:00-12:00 p.m., Levinson 40 Tuesday, September 16, 5:00-6:00 p.m., Levinson 40 Thursday, September 18, 4:30-5:30 p.m., Levinson 40 | Project leads, Primary leads, teams |
| Late September and October | Primary Leads Meet Monday, Sept.29, 430-530 in L40* Leads Meet with Standard Team Research Problem Identification and Solving Evidence Collection Writing Primary Leads Meet Friday, Oct. 10, 1045-1200 in Collins* Primary Leads Meet Thursday, Oct. 23, 330-500 in L40* | Primary leads Leads and teams |
| Monday, October 27 | Progress Report on Your Standard Due | Primary leads and teams |
| November | Primary Leads Meet Thursday, Nov. 20, 300-500 in L40* Feedback on Progress Report (individual) Continuing Work Problem Solving Writing Polishing | Primary leads Project leads Teams |
| Monday, December 1 | Final Report on Your Standard Due | Primary leads and teams |
| January—February | Revise final document Primary Leads meet Monday, Feb. 9, 300-500 in L40* | Kate Pluta and Jennifer Jett |
| February—March | Share with college community | Project Leads |
| March | Format for publication | Amber Chiang |
| April 9 | Midterm Report to district for inclusion in May board meeting | Project leads and Amber Chiang |
| Thursday, May 7 | Board of Trustees accepts the Midterm Report—Project completed | Kate Pluta |

*Written reports due to share and post to website

All Standard Teams must report on the following:		The Accreditation Standard

Most Standard Teams must also report on the following:	Eligibility Requirements

Recommendations

Some Standard Teams must also report on the following:	Commission Policies

Actionable Improvement Plans (AIPs)

Kate Pluta, September 10, 2014